## Sheet1
Defect ID | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Business/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Cycle 2 | UN_01 | System Testing | Release 1 | 2021-09-07 | Rohini |  | 4 | UniformStore_AddNewManufacturer |  | SEO URL field is supposed to be mandatory,because it holds a unique value for each manufacturer . | QA | 2021-09-07 17:47 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Before adding a manufacturer to the system ,enough data is not provided and provided details does not reflect any changes to the qualities of manufacturer.
2 | Cycle 1 | UN_02 | System Testing | Release 1 | 2021-09-07 | Rohini |  | 4 | UniformStore_AddNewManufacturer |  | Repeated addition of manufacturer is allowed with incompletely filled details | QA | 2021-09-07 11:22 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Duplication of manufacturer is possible when SEO URL field is not filled.
3 | Cycle 1 | UN_03 | System Testing | Release 1 | 2021-09-07 | Rohini |  | 4 | UniformStore_AddNewManufacturer |  | Sort order field does not really order the list as provided | QA | 2021-09-07 12:14 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Sorting doesn’t take place even after specifying the sort order.
4 | Cycle 1 | UN_04 | System Testing | Release 1 | 2021-09-07 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails |  | New Manufacturer is added successfully to the system even if all the necessary information is not given and does not make any difference regarding features of the Manufacturer. | QA | 2021-09-07 12:21 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Before updating a manufacturer to the system ,enough data is not provided and provided details does not reflect any changes to the qualities of manufacturer.
5 | Cycle 1 | UN_05 | System Testing | Release 1 | 2021-09-07 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails |  | Repeated addition of manufacturer is allowed with incompletely filled details | QA | 2021-09-07 12:24 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Duplication of manufacturer is possible when SEO URL field is not filled while updating.
3 | Cycle 1 | UN_06 | System Testing | Release 1 | 2021-09-07 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails |  | Sort order field does not really order the list as provided | QA | 2021-09-07 12:28 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Sorting doesn’t take place even after specifying the sort order.
0